## Year Planning
Year Planning
Quarter | Requirements Gathering | System Planning | Software Development | Testing
1/1/2023 Q1 | Analysis & Data collection
1/4/2023 Q2 |  | Technical analysis , Work breakdown and System design
1/7/2023 Q3 |  |  | CI/CD Pipeline, Frontend, Backend
1/10/2023 Q4 |  |  |  | UAT, Regression, Handover and Maintenance

## Quarter 1
Quarter Planning
Week | Requirements Gathering | Collecting Data | Data Cleansing
2023-01-01 | Identify deliverables and packages
2023-01-08
2023-01-15 |  | Collect data from sources
2023-01-22
2023-01-29
2023-02-05
2023-02-12 |  |  | Data cleansing
2023-02-19
2023-02-26
2023-03-05 |  |  | Verify Data
2023-03-12
2023-03-19
| Goals | Goals
| Gather high level requirements from stakeholders | Verify credible sources to gather data | Remove dirty data
Evaluate use case feasibility
Validate expected results

## Quarter 2
Quarter Planning
Week | Technical Analysis | Architect Solution | Work Breakdown
2023-04-01 | Provide early technical analysis for feasible check
2023-04-08
2023-04-15 |  | Enhance proposal
2023-04-22 |  | Architect system design
2023-04-29
2023-05-06
2023-05-13 |  |  | Start create work packages
2023-05-20 |  |  | Define development rules & practices
2023-05-27
2023-06-03
2023-06-10
2023-06-17
Goals
|  | System design | WBS
|  | System architecture | Create tickets
Diagrams

## Quarter 3
Quarter Planning
Week | Building CI/CD Pipe | Frontend Development | Backend Development
2023-07-01 | Start building CI/CD process template
2023-07-08
2023-07-15 |  | Create skeleton page
2023-07-22
2023-07-29
2023-08-05 |  | UI/UX enhancement
2023-08-12
2023-08-19 |  |  | Create REST APIs
2023-08-26
2023-09-02
2023-09-09 |  |  | Create dummy data
2023-09-16
| Goals | Goals | Goals
| Continuous integration | Template with routing to other pages | REST api
| Continuous deployment |  | Unit tests
CRUD operation

## Quarter 4
Quarter Planning
Week | Testing | Handover
2023-10-01 | UAT
2023-10-08
2023-10-15
2023-10-22
2023-10-29 | Regression Testing
2023-11-05
2023-11-12
2023-11-19 |  | Handover to client
2023-11-26
2023-12-03
2023-12-10 |  | Support & maintenance
2023-12-17
Goals